## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | In Progress | Hitbox for Weapon Removed | I: Issue | Hitbox for Player Weapon Was Removed | Unity | 2018-04-15 | 2018-04-25 | 2018-04-18 | It's in progress have to redo hitbox and possibly hitbox animation
2 | In progress | Invulnerability Frames | I: Issue | Adding I-Frames so Player can't die insanely fast | Unity-Scripts | 2018-04-18 | 2018-04-25 | N/A | Added the mechanic now need visual indicator
3 | New | Player Logistics | A: Action Item | Need to work out proper player speed and jumpPower | Unity | 2018-04-22 | 2018-04-28 | 2018-04-18 | Need to figure out the right balance and tweak the numbers
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete