## Sheet1
Phase 1 | Estimated Time Needed (Hours) | Actual Time Spent (in Hours) (Week 4) #line break is Alt + Enter | Actual Time Spent (in Hours) (Week 5) | Actual Time Spent (in Hours) (Week 6) | Actual Time Spent (in Hours) (Week 7) | Actual Time Spent (in Hours) (Week 8) | Actual Time Spent (in Hours) (Week 9)
Stage Design (platforms, graphics) | 6 | 2 | 1 | 0 | 0 | 0 | 0
Scene Transition | 5 | 2 | 1 | 0 | 0 | 0 | 0
Inventory System | 5 | 1 | 0 | 0 | 0 | 0 | 0
Graphical User Interface (GUI) | 3 | 1 | 0.5 | 0 | 0 | 0 | 0
Health System (add more values, new heart sprites) | 5 | 1 | 1 | 0 | 0 | 0 | 0
1st Play Test | 4 | 2 | 2 | 0 | 0 | 0 | 0
Enemy Design (new enemies) | 6 | 1 | 1 | 0 | 0 | 0 | 0
Level Design (obstacle placement) | 4 | 1 | 1 | 0 | 0 | 0 | 0
Tile Design | 3 | 0.5 | 0 | 0 | 0 | 0 | 0
Equipment System/Upgrade System (changing weapons) | 6 | 1 | 0 | 0 | 0 | 0 | 0
2nd Play Test | 5 | 0 | 0 | 0 | 0 | 0 | 0
Debug | 5 | 0 | 1 | 0 | 0 | 0 | 0
Actual Hours (Time Left) | 57 | 44.5 | 36 | 36 | 36 | 36 | 36
Estimated Hours (Time Left) | 57 | 47.5 | 38 | 28.5 | 19 | 9.5 | 0