## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Complete | Hitbox for Weapon Removed | I: Issue | Hitbox for Player Weapon Was Removed | Unity | 2018-04-15 | 2018-04-25 | 2018-04-18 | It's in progress have to redo hitbox and possibly hitbox animation
2 | Complete | Invulnerability Frames | I: Issue | Adding I-Frames so Player can't die insanely fast | Unity-Scripts | 2018-04-18 | 2018-04-25 | N/A | Added the mechanic now need visual indicator
3 | Complete | Player Logistics | A: Action Item | Need to work out proper player speed and jumpPower | Unity | 2018-04-22 | 2018-04-28 | 2018-04-29 | Need to figure out the right balance and tweak the numbers
4 | In Progress | Invulnerability Animation | A: Action Item | Add visual indicator so player knows when they are invlun | Unity | 2018-04-20 | 2018-04-27 | N/A | Not a top priority right now
5 | In progress | Spikes | I: Issue | Spikes appear to teleport player and based on where they are they don't work | Unity | 2018-04-25 | 2018-04-28 | 2018-05-04 | In progress with the teleportation but not with why some work and some don't
6 | Complete | Slime | I: Issue | Slime Slides Around | Unity | 2018-04-18 | 2018-05-09 | 2018-05-01
7 | New | Slime | I: Issue | Fix Trigger and Collider for Slime so they are frame perfect
8 | In progress | New AI For MiniBoss | A: Action Item | Develop new AI Possibly For MiniBoss | Unity | 2018-05-06 | 2018-05-15
9 | New | GameOver | A: Action Item | Develop Game Over Menu | Unity | 2018-05-02 | ?
10 | New | Player Control Config | A: Action Item | New Controls for player to customize | Unity | 2018-05-02 | ?
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete