## Sheet1
Phase 1 | Estimated Time Needed (Hours) | Actual Time Spent (in Hours) (Week 7) | Actual Time Spent (in Hours) (Week 8) | Actual Time Spent (in Hours) (Week 9)
Stage Design (platforms, graphics) | 2 | 1 | 0.5 | 0.5
Scene Transition | 1 | 1 | 0 | 0
Inventory System | 4 | 2 | 1 | 1
Graphical User Interface (GUI) | 0.5 | 0 | 0.5 | 0
Health System (add more values, new heart sprites) | 2 | 1 | 1 | 0
1st Play Test | 0 | 0 | 0 | 0
Enemy Design (new enemies) | 3 | 1 | 1 | 1
Level Design (obstacle placement) | 1 | 0 | 0.5 | 0.5
Tile Design | 1.5 | 1 | 0 | 0.5
Equipment System/Upgrade System (changing weapons) | 4.5 | 1.5 | 1.5 | 1.5
2nd Play Test | 4 | 1 | 1.5 | 1.5
Debug | 3 | 0 | 1.5 | 1.5
Actual Hours (Time Left) | 26.5 | 17 | 8 | 0
Estimated Hours (Time Left) | 26.5 | 17.6667 | 8.8333 | 0